## Sheet1
TEAM MEMBERS | Resource ID's | ROLES | PROJECT PLANNING | PROJECT MEETING | CONTRIBUTION IN EACH SPRINT |  |  | MEETINGS (hrs) |  |  |  | TOTAL EFFORT(hrs) | % of contribution
[5 empty] | SPRINT 1(hrs) | SPRINT 2 (hrs) | SPRINT 3 (hrs) | REVIEW | RETROSPECTIVE | FEEDBACK | BUFFER(10)
NIKHIL | R8 | ANALYST/DEVELOPER | 30 | 7 | 38 | 40 |  | 3 | 4 | 3
AKSHAY | R4 | TESTER/ DEVELOPER | 30 | 6 | 38 | 36 |  | 3 | 4 | 3
PANCHAJANYA | R7 | TESTER/ DEVELOPER | 30 | 6 | 32 | 36 |  | 3 | 4 | 3
SHIVA | R1 | PRODUCT OWNER /DEVELOPER | 30 | 6 | 35 | 42 |  | 3 | 4 | 3
ANVITHA | R3 | SCRUM MASTER /DEVELOPER | 30 | 7 | 35 | 40 |  | 3 | 4 | 3
HARINI | R6 | DESIGNER/DEVELOPER | 30 | 6 | 32 | 37 |  | 3 | 4 | 3
CHILLA KARTHIK | R2 | DESIGNER/DEVELOPER | 30 | 6 | 33 | 39 |  | 3 | 4 | 3
SAMHITH | R5 | ANALYST/DEVELOPER | 30 | 6 | 33 | 39 |  | 3 | 4 | 3
TOTAL TIME |  |  | 240 | 50 | 276 | 309 |  | 24 | 32 | 24
USER POINTS |  | 1 User Point = 3 hours |  |  | 92 | 103