## Sheet1
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 |  | Column15 | Column16 | Column17
User stories | Resource Names |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 |  |  | Individual Hours
Privacy Policy | Nikhil |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0; Column8 Day 5: 0 |  |  | 0
| Akshay |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0; Column8 Day 5: 0 |  |  | 0
| Shiva |  | 2 | 3 | 2 | 0 | 2 |  | User Story Completed | [5 empty] | 9
| Anvitha |  | Column4 Day 1: 3; Column5 Day 2: 4; Column6 Day 3: 1; Column7 Day 4: 0; Column8 Day 5: 1 |  |  | 9
| Chilla |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0; Column8 Day 5: 0 |  |  | 0
| Pancha |  | Column4 Day 1: 2; Column5 Day 2: 2; Column6 Day 3: 1; Column7 Day 4: 1; Column8 Day 5: 0 |  |  | 6
| Samhith |  | Column4 Day 1: 1; Column5 Day 2: 2; Column6 Day 3: 1; Column7 Day 4: 2; Column8 Day 5: 3 |  |  | 9
| Harini |  | Column4 Day 1: 1; Column5 Day 2: 0; Column6 Day 3: 4; Column7 Day 4: 1; Column8 Day 5: 0 |  |  | 6
| Team hours |  | Column4 Day 1: 9; Column5 Day 2: 11; Column6 Day 3: 9; Column7 Day 4: 4; Column8 Day 5: 6 |  |  | 39
Search | Nikhil |  |  |  | 0 | 1 | 2 | 3 | 1 | 0 | 2 | 3
| Akshay |  |  |  | 1 | 1 | 4 | 4 | 3 | 4 | 2 | 2
| Shiva |  |  |  | 0 | 0 | 0 | 3 | 3 | 0 | 1 | 3
| Anvitha |  |  |  | 0 | 0 | 2 | 2 | 2 | 0 | 3 | 2
| Chilla |  |  |  | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 3
| Pancha |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
| Samhith |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Harini |  |  |  | 0 | 1 | 1 | 2 | 2 | 0 | 3 | 2
| Team hours |  |  |  | 1 | 7 | 9 | 14 | 13 | 4 | 15 | 18 |  | 81
Product quantity | Nikhil | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Akshay | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Shiva | [5 empty] | 0 | 0 | 1 | 4 | 1 | 0
| Anvitha | [5 empty] | 0 | 0 | 2 | 4 | 0 | 0
| Chilla | [5 empty] | 4 | 4 | 2 | 4 | 1 | 0
| Pancha | [5 empty] | 1 | 1 | 4 | 3 | 0 | 0 |  | User story completed
| Samhith | [5 empty] | 1 | 1 | 4 | 4 | 4 | 1
| Harini | [5 empty] | 0 | 0 | 2 | 4 | 0 | 0
| Team hours | [5 empty] | 6 | 6 | 15 | 23 | 6 | 1 |  | 57
Offers | Nikhil |  | Column4 Day 1: 4; Column5 Day 2: 3; Column6 Day 3: 0; Column7 Day 4: 2 |  |  | 9
| Akshay |  | Column4 Day 1: 4; Column5 Day 2: 0; Column6 Day 3: 2; Column7 Day 4: 3 |  |  | 9
| Shiva |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0 |  |  | 0
| Anvitha |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0; Column9 Day 6: User Story Completed |  |  | 0
| Chilla |  | Column4 Day 1: 3; Column5 Day 2: 4; Column6 Day 3: 2; Column7 Day 4: 0 |  |  | 9
| Pancha |  | Column4 Day 1: 0; Column5 Day 2: 0; Column6 Day 3: 0; Column7 Day 4: 0 |  |  | 0
| Samhith |  | Column4 Day 1: 3; Column5 Day 2: 2; Column6 Day 3: 2; Column7 Day 4: 2 |  |  | 9
| Harini |  | Column4 Day 1: 3; Column5 Day 2: 2; Column6 Day 3: 0; Column7 Day 4: 1 |  |  | 6
| Team hours |  | Column4 Day 1: 17; Column5 Day 2: 11; Column6 Day 3: 6; Column7 Day 4: 8 |  |  | 42
Subscription | Nikhil | [5 empty] | 1 | 1 | 3 | 4 | 1 | 1
| Akshay | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Shiva | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Anvitha | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Chilla | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Pancha | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Samhith | [5 empty] | 0 | 0 | 0 | 0 | 1 | 1
| Harini | [5 empty] | 0 | 0 | 0 | 0 | 2 | 1
| Team hours | [5 empty] | 1 | 1 | 3 | 4 | 9 | 8 |  | 26
Social Connectivity | Nikhil |  | Column7 Day 4: 0; Column8 Day 5: 0; Column9 Day 6: 0 |  |  | 0
| Akshay |  | Column7 Day 4: 0; Column8 Day 5: 0; Column9 Day 6: 0 |  |  | 0
| Shiva |  | Column7 Day 4: 3; Column8 Day 5: 2; Column9 Day 6: 1 |  |  | 6
| Anvitha |  | Column7 Day 4: 3; Column8 Day 5: 1; Column9 Day 6: 2; Column11 Day 8: User Story Completed |  |  | 0
| Chilla |  | Column7 Day 4: 0; Column8 Day 5: 0; Column9 Day 6: 0 |  |  | 0
| Pancha |  | Column7 Day 4: 3; Column8 Day 5: 3; Column9 Day 6: 3 |  |  | 9
| Samhith |  | Column7 Day 4: 0; Column8 Day 5: 0; Column9 Day 6: 3 |  |  | 6
| Harini |  | Column7 Day 4: 1; Column8 Day 5: 3; Column9 Day 6: 2 |  |  | 6
| Team hours |  | Column7 Day 4: 10; Column8 Day 5: 9; Column9 Day 6: 11 |  |  | 30
|  |  | 26 | 22 | 16 | 29 | 31 | 32 | 31 | 31 | 30 | 27 |  | 275

## Sheet2
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14
S.NO |  | User Stories |  | Tasks |  | Responsible person |  | Estimated Effort(hrs) |  | Estimated Effort( User Points) |  | Contribution
1 |  | Privacy policy |  | Data gathering for privacy policy |  | Samhith |  | 9 |  | 3
|  |  |  | policy design |  | Harini |  | 6 |  | 2
|  |  |  | Policy page element development |  | Shiva,Anvitha(P1) |  | 18 |  | 6 |  | 3+3
|  |  |  | Privacy Page verification |  | Panchagenya |  | 6 |  | 2
[8 empty] | 39 |  | 13
2 |  | Search |  | Data gathering about the elements to be shown with search option |  | Nikhil |  | 6 |  | 2
|  |  |  | Interface design |  | Harini |  | 9 |  | 3
|  |  |  | Design of Data base interaction |  | Karteek |  | 6 |  | 2
|  |  |  | Search option front end development |  | Shiva,Anvitha (P1) |  | 12 |  | 4 |  | 2+2
|  |  |  | Development for connecting the backend with search option |  | Nikhil,Akshay |  | 15 |  | 5 |  | 1+4
|  |  |  | Search option functionality testing |  | Akshay,Panchagenya |  | 12 |  | 4 |  | 2+2
|  |  |  | Search option link testing (Accessibility testing) |  | Akshay |  | 6 |  | 2
[8 empty] | 66 |  | 22
3 |  | Product quantity |  | accessing information about the quantity attribute of a product |  | Samhith |  | 9 |  | 3
|  |  |  | User Interface design |  | Harini |  | 6 |  | 2
|  |  |  | Database design |  | Karteek |  | 9 |  | 3
|  |  |  | development for accessing the information of Product quantity |  | Shiva,Anvitha |  | 12 |  | 4 |  | 2+2
|  |  |  | retrieving the information about quantity (back-front end connectivity) |  | samhith,Karteek |  | 12 |  | 4 |  | 2+2
|  |  |  | Quantity attribute validation and verification |  | Panchagenya |  | 9 |  | 3
[8 empty] | 57 |  | 19
4 |  | Social Connectivity |  | Data gathering about the networking sites to be provided in the site |  | Samhith |  | 3 |  | 1
|  |  |  | Interface and relationship design |  | harini |  | 6 |  | 2
|  |  |  | connecting the network sites and their development in the main site |  | Anvitha,Shiva (P1) |  | 12 |  | 4 |  | 2+2
|  |  |  | functionality testing |  | Panchagenya |  | 9 |  | 3
[8 empty] | 30 |  | 10
5 |  | Subscription |  | data gathering about the users and information to be provided |  | Nikhil |  | 6 | 4 | 2
|  |  |  | Interface design |  | harini |  | 9 | 9 | 3
|  |  |  | Backend connectivity design |  | karteek |  | 9 | 6 | 3
|  |  |  | Subscription option development in the main site |  | Shiva,Anvitha(P1) |  | 12 | 9 | 4 |  | 2+2
|  |  |  | back end connectiviting and message passing development |  | Nikhil,Samhith(P4) |  | 9 | 6 | 3 |  | 2+1
|  |  |  | Testing the entire functionality of the user story |  | Akshay,Panchagenya |  | 15 | 12 | 5 |  | 1+4
[8 empty] | 60 |  | 20
46
6 |  | offers |  | information gathering about the offeres to be provided in the site and for the user |  | Nikhil |  | 6 |  | 2
|  |  |  | desgning the interface of offers |  | karteek,Harini |  | 15 |  | 5 |  | (3+2)
0 |  |  |  | developing the feature |  | Samhith,Nikhil(P4) |  | 12 |  | 4 |  | 3+1
|  |  |  | Functionality testing and validation of the feature |  | Akshay |  | 9 |  | 3
14
42