## Sheet1
TEAM MEMBERS | ROLES | PROJECT PLANNING | PROJECT MEETING | CONTRIBUTION IN EACH SPRINT |  |  |  | MEETINGS (hrs) |  |  |  | TOTAL EFFORT(hrs) | % of contribution
|  |  |  | SPRINT 1(hrs) | SPRINT 2 (hrs) | SPRINT 3 (hrs) | MEETING | REVIEW | RETROSPECTIVE | FEEDBACK | BUFFER(10)
NIKHIL | ANALYST/DEVELOPER | 30 | 7 | 38 | 40 | 31 | 3 | 4 | 4 | 3 | 10 | 170
AKSHAY | TESTER/ DEVELOPER | 30 | 6 | 38 | 36 | 36 | 3 | 4 | 4 | 3 | 10
PANCHA | TESTER/ DEVELOPER | 30 | 6 | 32 | 36 | 42 | 3 | 4 | 4 | 3 | 10
SHIVA | PRODUCT OWNER /DEVELOPER | 30 | 6 | 35 | 42 | 33 | 3 | 4 | 4 | 3 | 10
ANIVITA | SCRUM MASTER /DEVELOPER | 30 | 7 | 35 | 40 | 34 | 3 | 4 | 4 | 3 | 10
HARINI | DESIGNER/DEVELOPER | 30 | 6 | 32 | 37 | 41 | 3 | 4 | 4 | 3 | 10
CHILLA | DESIGNER/DEVELOPER | 30 | 6 | 33 | 39 | 38 | 3 | 4 | 4 | 3 | 10
SAMHITH | ANALYST/DEVELOPER | 30 | 6 | 33 | 39 | 38 | 3 | 4 | 4 | 3 | 10
TOTAL TIME |  | 240 | 50 | 276 | 309 | 293 | 24 | 32 | 32 | 24 | 80
USER POINTS |  |  |  | 92 | 103 | 98